## Sheet1
| W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
No. of deadlines (excl. project work) | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Timetabled hours of on-campus activities (excl. project related activities) | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 10 | 0
Expected number of hours for private study (excl. project related activities) | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 22 | 10
Important Project Deadlines/Deliverables | Project scoping; initial objectives; proposal and H&S planning | Preliminary proposal, project outline, initial Gantt and H&S risk assessment | Architecture refinement; chassis measurement; CAD, PCB and wiring planning | CAD/3D print planning; PCB layout; PlatformIO and ESP32 setup preparation | CAN bus, six-motor initialisation and MPU6050 DMP bring-up | PID framework: roll, yaw, leg length and leg-angle regulation | Ground detection, airborne wheel disable and landing cushioning logic | Angle protection, stand-up state machine, PCB soldering and wiring harness work | Jump behaviour; printed-part modification; motor lead and connector reliability checks | Xbox BLE controller integration and manual input mapping | Motor calibration, NVS persistence, voltage monitoring; draft intro/methodology due | Christmas reduced work: UART2 command queue and documentation cleanup
Expected number of hours for project work (incl. project meeting time) | 8 | 10 | 10 | 12 | 14 | 14 | 13 | 14 | 12 | 12 | 10 | 6