| Project Title: | B-BOT: WiFi-enabled self-balancing wheel-legged robot |  | Submission Date: | 25 April 2026 |  |
| --- | --- | --- | --- | --- | --- |
| Student Name: | Botao Su |  |  |  |  |

| Project Risk | Severity |  |  | Potential |  |  | Score (Severity x Potential) | Mitigation Measures |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | L | M | H | L | M | H | L=1, M=2, H=3 |  |
| Final robot hardware, wiring or mechanical integration is delayed, limiting the time available for physical balance tests. |  |  | X |  | X |  | 6 | Split work into bench-verifiable subsystems; bring up ESP32, camera and WiFi command path before full robot availability; prioritise E1-E4/E9 physical tests once hardware is available; keep provisional analysis clearly marked until replaced. |
| Balance tuning may remain unstable, causing protection events or failed repeated trials. |  |  | X |  | X |  | 6 | Use incremental gain changes, supported bench tests, low-energy trials, protection-state logging and repeatable pass criteria; report failed trials instead of hiding them; keep stabilising loop local to ESP32. |
| ESP32, CAN motor feedback, IMU calibration or firmware integration faults may block reliable testing. |  |  | X |  | X |  | 6 | Test IMU, CAN feedback, command parsing and motor output separately; use USB serial logs and PlatformIO builds; commit working firmware states; keep rollback points and record calibration assumptions. |
| WiFi TCP command latency, disconnection or host-side failure may affect teleoperation tests or demonstration reliability. |  | X |  |  | X |  | 4 | Keep WiFi outside the balance loop; use ACK-based latency measurement, direct-command watchdog, TCP idle timeout and full-stop on disconnect; demonstrate safe fallback with manual or dry-run modes. |
| ROS 2 WiFi camera module or MediaPipe recognition may be unreliable because of frame rate, lighting, gesture ambiguity or framing. |  | X |  |  | X |  | 4 | Use local preview, dry-run mode, gesture confusion matrix, command debouncing/gating and manual control fallback; treat vision as supervisory teleoperation only. |
| Insufficient measured data may be available before writing, causing provisional or synthetic values to remain in the final submission. |  |  | X |  | X |  | 6 | Maintain an explicit provisional-data policy; mark all synthetic rows; prioritise replacement of E1, E2, E3, E4 physical response and E9; avoid final claims based on provisional data. |
| Scope creep from full autonomy, advanced navigation, complex jumping or companion-computer features may dilute the core contribution. |  | X |  |  |  | X | 6 | Freeze the final contribution around embedded balance, WiFi TCP safety and ROS 2 vision teleoperation; move Raspberry Pi/Jetson autonomy and advanced locomotion to future work; align all experiments to O1-O3. |
| Loss of source code, experiment logs, figures or planning evidence may reduce traceability and require repeated work. |  |  | X |  | X |  | 6 | Use Git/GitHub commits, maintain Progress.md, store raw CSV files under Report/appendices/E_data, keep generated figures and document major decisions after each work session. |
| Examination periods, vacation gaps and report-deadline pressure may reduce continuous progress and increase integration risk. |  | X |  |  |  | X | 6 | Reconstruct and update the Gantt chart; reserve final sprint time for testing/report integration; narrow scope to measurable evidence; use weekly plan and deviation notes in Appendix B. |
| Third-party code, libraries or reused reference material may not be clearly attributed, creating academic integrity or reproducibility risk. |  |  | X |  | X |  | 6 | Maintain repository README, source-attribution table, citations for libraries and algorithms, and clear distinction between original code, modified code and third-party components. |